## Sheet1
Phase | Tasks | Estimated Time ( Hours) | Actual Time( Hours)
Requirements | Analyze requirements, confirm architecture, define microservice boundaries. | 2 | 2.5
System Design | Create system architecture, component diagram, data models, API specs. | 2 | 3
Setup Solution | Create .NET Core solution with separate projects for Order, Payment, Email, Production, and Common. | 2 | 2
Core Features | Implement OrderService with In-Memory DB, sample data seeder, order search API. | 2 | 2
Search and Checkout Logic | Implement checkout workflow with HttpClientFactory calling mock services. | 3 | 3.5
Mock Services | Implement PaymentService, EmailService, ProductionService with mock endpoints. | 2 | 1.5
Integration | Configure service URLs, add APIResponse wrapper, test inter-service communication. | 1.5 | 2
Documentation | Write Assumption, SystemDesign, API endpoints doc, and delivery plan. | 2 | 2
Review & Test | Functional testing of all scenarios (success, payment fail, production fail). | 1 | 1.5
TOTAL |  | 17.5 | 20